## ProjectSchedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Crash Avoidance System | [6 empty] | SIMPLE GANTT CHART by Vertex42.com
Enter Company Name in cell B2. | X-Y-Z | [6 empty] | https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. | Project Lead | Project Start: |  |  | 2021-01-01
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  |  | 2021-01-01 |  |  | 2021-01-01 |  |  |  |  | 2021-02-05 |  |  |  | 2021-03-05 |  |  |  | 2021-04-02 |  |  |  |  | 2021-05-07 |  |  |  | 2021-06-04 |  |  |  | 2021-07-02 |  |  |  |  | 2021-08-06 |  |  |  | 2021-09-03 |  |  |  |  | 2021-10-08 |  |  |  | 2021-11-05 |  |  |  | 2021-12-03 |  |  |  |  | 2022-01-07 |  |  |  | 2022-02-04 |  |  |  | 2022-03-04 |  |  |  |  | 2022-04-08 |  |  |  | 2022-05-06 |  |  |  | 2022-06-03 |  |  |  |  | 2022-07-08 |  |  |  | 2022-08-05 |  |  |  | 2022-09-02 |  |  |  |  | 2022-10-07 |  |  |  | 2022-11-04 |  |  |  | 2022-12-02 |  |  |  |  | 2023-01-06 |  |  |  | 2023-02-03 |  |  |  | 2023-03-03 |  |  |  |  | 2023-04-07 |  |  |  | 2023-05-05 |  |  |  | 2023-06-02 |  |  |  |  | 2023-07-07 |  |  |  | 2023-08-04 |  |  |  |  | 2023-09-08 |  |  |  | 2023-10-06 |  |  |  | 2023-11-03 |  |  |  |  | 2023-12-08 |  |  |  | 2024-01-05 |  |  |  | 2024-02-02 |  |  |  | 2024-03-01 |  |  |  |  | 2024-04-05 |  |  |  | 2024-05-03 |  |  |  |  | 2024-06-07 |  |  |  | 2024-07-05 |  |  |  | 2024-08-02 |  |  |  |  | 2024-09-06 |  |  |  | 2024-10-04 |  |  |  | 2024-11-01 |  |  |  |  | 2024-12-06 |  |  |  | 2025-01-03
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2021-01-01 to 2025-01-24
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | WBS | PROGRESS | START | END | DAYS | bar: 2021-01-01 to 2025-01-24
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Program Milestones
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Development of Crash Avoidance System
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Program Event 1 | Develop Crash Avoidance System (CAS) |  | 0% | 2021-01-01 | 2021-12-31 | 365
| Preliminary Design Review (PDR) |  |  | 0% | 2021-01-01 | 2021-02-05
| Critical Design Review (CDR) |  |  | 0% | 2021-02-05 | 2021-04-05
System Engineering - Example IMP, IMS, and WBS
| Significant Accomplishment A | Complete System Engineering Tasks | A | 0% | 2021-01-01 | 2021-12-31
| Significant Accomplishment A.1 | Complete System Engineering Management Tasks | A.1 | 0% | 2021-01-01 | 2021-12-31
Complete
| Significant Accomplishment A.2 | Complete System Engineering Support Tasks | A.2 | 0% | 2021-01-01 | 2021-04-05
| Accomplishment A.2.1 | Support Preliminary Design Review (PDR) | A.2.1 | 0% | 2021-04-01 | 2021-04-09
| Accomplishment A.2.2 | Support Critical Design Review (CDR) | A.2.2 | 0% | 2021-04-01 | 2021-04-09
Complete
| Significant Accomplishment A.3 | Complete System Engineering Development Tasks | A.3 | 0% | 2021-01-01 | 2021-12-31
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Accomplishment A.3.0 | Reuse & Modify CAS POD Requirements | A.3.0 | 50% | 2021-01-01 | 2021-02-01 | 32
| Task A.3.0.1 | LIFT POD Requirements (reuse) | A.3.0 | 100% | 2021-01-01 | 2021-01-15
| Task A.3.0.2 | MODIFY POD Requirements | A.3.0 | 0% | 2021-01-15 | 2021-02-01
| Accomplishment A.3.1 | Develop FMK & High-Risk Requirements | A.3.1 | 0% | 2021-02-01 | 2021-04-21
| Task A.3.1.1 | Complete Initial Requirement Development | A.3.1 | 0% | 2021-02-01 | 2021-03-01
| Task A.3.1.2 | Complete Final Requirement Development | A.3.1 | 0% | 2021-03-01 | 2021-04-01
| Accomplishment A.3.2 | Develop CAS GEO Avoidance System Requirements | A.3.2 | 0% | 2021-04-01 | 2021-06-01
| Task A.3.2.1 | Complete Initial Requirement Development | A.3.2 | 0% | 2021-04-01 | 2021-05-01
| Task A.3.2.2 | Complete Final Requirement Development | A.3.2 | 0% | 2021-05-01 | 2021-06-01
Continue pattern until all Builds/Iterations are defined.
| Accomplishment A.3.3 | Develop CAS Airborne Avoidance System Requirements | A.3.3 | 0% | 2021-06-01 | 2021-08-01
| Task A.3.3.1 | Complete Initial Requirement Development | A.3.3 | 0% | 2021-06-01 | 2021-07-01
| Task A.3.3.2 | Complete Final Requirement Development | A.3.3 | 0% | 2021-07-01 | 2021-08-01
| Significant Accomplishment A.4 | Complete System Engineering Test Tasks | A.4 | 0% | 2021-01-01 | 2021-12-31
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Accomplishment A.4.0 | Complete System Integration for POD | A.4.0 | 0% | 2021-05-01 | 2021-06-01 | 32
| Task A.4.0.1 | Create System Integration Regression Test for POD | A.4.0 | 0% | 2021-05-01 | 2021-06-01
| Task A.4.0.1.1 | Develop Regression Test Procedure | A.4.0 | 0% | 2021-05-01 | 2021-05-10
| Task A.4.0.1.2 | Dry-Run Regression Test Procedure | A.4.0 | 0% | 2021-05-10 | 2021-05-20
| Task A.4.0.1.3 | Conduct Regression Test Procedure | A.4.0 | 0% | 2021-05-20 | 2021-06-01
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Accomplishment A.4.1 | Complete System Integration for FMK Enhancements | A.4.1 | 0% | 2021-06-01 | 2021-08-01 | 62
| Task A.4.1.1 | Create System Integration Test for FMK Features | A.4.1 | 0% | 2021-06-01 | 2021-07-01
| Task A.4.1.1.1 | Develop Test Procedure - FMK Threads | A.4.1 | 0% | 2021-06-01 | 2021-06-10
| Task A.4.1.1.2 | Dry-Run Test Procedure - FMK Threads | A.4.1 | 0% | 2021-06-10 | 2021-06-20
| Task A.4.1.1.3 | Conduct Test Procedure - FMK Threads | A.4.1 | 0% | 2021-06-20 | 2021-07-01
| Task A.4.1.2 | Create System Performance Test for FMK Features | A.4.1 | 0% | 2021-07-01 | 2021-08-01
| Task A.4.1.2.1 | Develop Test Procedure - Performance Threads | A.4.1 | 0% | 2021-07-01 | 2021-07-10
| Task A.4.1.2.2 | Dry-Run Test Procedure - Performance Threads | A.4.1 | 0% | 2021-07-10 | 2021-07-20
| Task A.4.1.2.3 | Conduct Test Procedure - Performance Threads | A.4.1 | 0% | 2021-07-20 | 2021-08-01
| Accomplishment A.4.2 | Complete System Integration for CAS GEO Avoidance Features | A.4.2 | 0% | 2021-08-01 | 2021-10-01
| Task A.4.2.0 | Create CAS GEO Avoidance System | A.4.2 | 0% | 2021-08-01 | 2021-10-01
| Task A.4.2.1 | Create System Integration Test for GEO Avoidance Features | A.4.2 | 0% | 2021-08-01 | 2021-10-01
| Task A.4.2.1.1 | Develop Test Procedure - GEO Avoidance Threads | A.4.2 | 0% | 2021-08-01 | 2021-08-10
| Task A.4.2.1.2 | Dry-Run Test Procedure - GEO Avoidance Threads | A.4.2 | 0% | 2021-08-10 | 2021-08-20
| Task A.4.2.1.3 | Conduct Test Procedure - GEO Avoidance Threads | A.4.2 | 0% | 2021-08-20 | 2021-09-01
| Task A.4.2.2 | Create System Performance Test for GEO Avoidance Features | A.4.2 | 0% | 2021-09-01 | 2021-10-01
| Task A.4.2.2.1 | Develop Test Procedure - Performance Threads | A.4.2 | 0% | 2021-09-01 | 2021-09-10
| Task A.4.2.2.2 | Dry-Run Test Procedure - Performance Threads | A.4.2 | 0% | 2021-09-10 | 2021-09-20
| Task A.4.2.2.3 | Conduct Test Procedure - Performance Threads | A.4.2 | 0% | 2021-09-20 | 2021-10-01
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Accomplishment A.4.3 | Complete System Integration for CAS Airborne Avoidance Features | A.4.3 | 0% | 2021-10-01 | 2021-12-01 | 62
| Task A.4.3.1 | Create System Integration Test for CAS Airborne Avoidance Features | A.4.3 | 0% | 2021-10-01 | 2021-11-01
| Task A.4.3.1.1 | Develop Test Procedure - CAS Airborne Avoidance Threads | A.4.3 | 0% | 2021-10-01 | 2021-11-01
| Task A.4.3.1.2 | Dry-Run Test Procedure - CAS Airborne Avoidance Threads | A.4.3 | 0% | 2021-10-10 | 2021-10-20
| Task A.4.3.1.3 | Conduct Test Procedure - CAS Airborne Avoidance Threads | A.4.3 | 0% | 2021-10-20 | 2021-11-01
| Task A.4.3.2 | Create System Performance Test for CAS Airborne Avoidance Features | A.4.3 | 0% | 2021-11-01 | 2021-12-01
| Task A.4.2.2.1 | Develop Test Procedure - Performance Threads | A.4.3 | 0% | 2021-11-01 | 2021-11-10
| Task A.4.2.2.2 | Dry-Run Test Procedure - Performance Threads | A.4.3 | 0% | 2021-11-10 | 2021-11-20
| Task A.4.2.2.3 | Conduct Test Procedure - Performance Threads | A.4.3 | 0% | 2021-11-20 | 2021-12-01
| Significant Accomplishment C | Complete Software (SW) Engineering Tasks | C | 0% | 2021-01-01 | 2021-12-31
| Significant Accomplishment C.1 | Complete SW Engineering Management Tasks | C.1 | 0% | 2021-01-01 | 2021-12-31
Complete
| Significant Accomplishment C.2 | Complete SW Engineering Support Tasks | C.2 | 0% | 2021-01-01 | 2021-04-05
Complete
| Significant Accomplishment C.3 | Complete SW Engineering Development Tasks | C.3 | 0% | 2021-01-01 | 2021-12-31
| Accomplishment C.3.0 | Port SW Baseline and Validate Existing Avionic Interfaces | C.3.0 | 0% | 2021-01-01 | 2021-03-01
| Task C.3.0.1 | Establish SW Baseline for CAS | C.3.0 | 0% | 2021-01-01 | 2/1/21
| Task C.3.0.1.1 | Port SW Baseline | C.3.0 | 0% | 2021-01-01 | 2021-01-10
| Task C.3.0.1.2 | Compile/Run SW Baseline | C.3.0 | 0% | 2021-01-10 | 2021-01-20
| Task C.3.0.1.3 | Update SW Baseline Adaptation Data | C.3.0 | 0% | 2021-01-20 | 2021-02-01
| Task C.3.0.2 | Develop SW Regression Test to Validate Avionic Interfaces | C.3.0 | 0% | 2021-02-01 | 3/1/21
| Task C.3.0.2.1 | Develop Regression Test Procedure | C.3.0 | 0% | 2021-02-01 | 2021-02-10
| Task C.3.0.2.2 | Dry-Run Regression Test Procedure | C.3.0 | 0% | 2021-02-10 | 2021-02-20
| Task C.3.0.2.3 | Conduct Regression Test Procedure | C.3.0 | 0% | 2021-02-20 | 2021-03-01
| Accomplishment C.3.1 | Complete FMK & High Risk Features | C.3.1 | 0% | 2021-03-01 | 2021-07-01
Complete
| Accomplishment C.3.2 | Complete Geographic Object (GEO) Detection Subsystem | C.3.2 | 0% | 2021-04-01 | 2021-06-01
| Accomplishment C.3.2.1 | Complete GEO Detection - Use Case 1 | C.3.2 | 0% | 2021-04-01 | 2021-05-10
| Task C.3.2.1.1 | Task Name - SW Preliminary Model/Design | C.3.2 | 0% | 2021-04-01 | 2021-04-10
| Task C.3.2.1.2 | Task Name - SW Detailed Model/Design | C.3.2 | 0% | 2021-04-10 | 2021-04-20
| TaskC.3.2.1.3 | Task Name - SW Code & Unit Test | C.3.2 | 0% | 2021-04-21 | 2021-05-01
| Task C.3.2.1.4 | Task Name - SW Integration & Test | C.3.2 | 0% | 2021-05-01 | 2021-05-10
| Accomplishment C.3.2.2 | Complete GEO Detection - Use Case 2 | C.3.2 | 0% | 2021-04-01 | 2021-06-01
| Task C.3.2.2.1 | Task Name - SW Preliminary Model/Design | C.3.2 | 0% | 2021-04-01 | 2021-04-10
| Task C.3.2.2.2 | Task Name - SW Detailed Model/Design | C.3.2 | 0% | 2021-04-11 | 2021-04-20
| TaskC.3.2.2.3 | Task Name - SW Code & Unit Test | C.3.2 | 0% | 2021-04-21 | 2021-05-01
| Task C.3.2.2.4 | Task Name - SW Integration & Test | C.3.2 | 0% | 2021-05-01 | 2021-05-10
Continue pattern until all Use Cases within Build are defined.
| Accomplishment C.3.3 | Complete Airborne Detection Subsystem | C.3.3 | 0% | 2021-06-01 | 2021-08-01
| Task C.3.2.3.1 | Task Name - SW Preliminary Model/Design | C.3.3 | 0% | 2021-06-01 | 2021-06-15
| Task C.3.2.3.2 | Task Name - SW Detailed Model/Design | C.3.3 | 0% | 2021-06-15 | 2021-07-01
| Task C.3.2.3.3 | Task Name - SW Code & Unit Test | C.3.3 | 0% | 2021-07-01 | 2021-07-15
| Task C.3.2.3.4 | Task Name - SW Integration & Test | C.3.3 | 0% | 2021-07-15 | 2021-08-01
| Significant Accomplishment C.4 | Complete SW Engineering Test Tasks | C.4 | 0% | 2021-01-01 | 2021-12-31
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Accomplishment C.4.0 | Complete SW Integration for POD | C.4.0 | 0% | 2021-05-01 | 2021-06-01 | 32
| Task C.4.0.1 | Develop SW Regression Test to Validate Avionic Interfaces | C.4.0 | 0% | 2021-05-01 | 2021-06-01
| Task C.4.0.1.1 | Develop Regression Test Procedure | C.4.0 | 0% | 2021-05-01 | 2021-05-10
| Task C.4.0.1.2 | Dry-Run Regression Test Procedure | C.4.0 | 0% | 2021-05-10 | 2021-05-20
| Task C.4.0.1.3 | Conduct Regression Test Procedure | C.4.0 | 0% | 2021-05-20 | 2021-06-01
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Accomplishment C.4.1 | Complete SW Integration for FMK Enhancements | C.4.1 | 0% | 2021-06-01 | 2021-08-01 | 62
| Task C.4.1.1 | Create SW Integration Test for FMK Enhancements | C.4.1 | 0% | 2021-06-01 | 2021-07-01
| Task C.4.1.1.1 | Develop FMK Enhancement Test Procedure | C.4.1 | 0% | 2021-06-01 | 2021-06-10
| Task C.4.1.1.2 | Dry-Run FMK Enhancement Test Procedure | C.4.1 | 0% | 2021-06-10 | 2021-06-20
| Task C.4.1.1.3 | Conduct FMK Enhancement Test Procedure | C.4.1 | 0% | 2021-06-20 | 2021-07-15
| Task C.4.1.1.4 | Update Regression Test Suite | C.4.1 | 0% | 2021-07-15 | 2021-08-01
Continue pattern until all Builds/Iterations are defined.
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Accomplishment C.4.2 | Complete SW Integration for GEO Detection Features | C.4.2 | 0% | 2021-08-01 | 2021-09-01 | 32
| Task C.4.2.1 | Create SW Integration Test for GEO Detection Features | C.4.2 | 0% | 2021-06-01 | 2021-06-15
| Task C.4.2.1.1 | Develop FMK Enhancement Test Procedure | C.4.2 | 0% | 2021-06-15 | 2021-07-01
| Task C.4.2.1.2 | Dry-Run FMK Enhancement Test Procedure | C.4.2 | 0% | 2021-07-01 | 2021-07-15
| Task C.4.2.1.3 | Conduct FMK Enhancement Test Procedure | C.4.2 | 0% | 2021-07-15 | 2021-08-01
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Accomplishment C.4.3 | Complete SW Integration for Airborne Detection Features | C.4.3 | 0% | 2021-06-01 | 2021-09-01 | 93
| Task C.4.3.1 | Create SW Integration Test for Airborne Detection Features | C.4.3 | 0% | 2021-06-01 | 2021-06-15
| Task C.4.3.1.1 | Develop FMK Enhancement Test Procedure | C.4.3 | 0% | 2021-06-15 | 2021-07-01
| Task C.4.3.1.2 | Dry-Run FMK Enhancement Test Procedure | C.4.3 | 0% | 2021-07-01 | 2021-07-15
| Task C.4.3.1.3 | Conduct FMK Enhancement Test Procedure | C.4.3 | 0% | 2021-07-15 | 2021-08-01
| Significant Accomplishment C.5 | Complete SW Engineering Maintenance Tasks | C.5 | 0% | 2021-09-01 | 2021-12-31
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | In-Flight Test of Crash Avoidance System (IFTCAS)
| Program Event 2 | Develop In-Flight Test of Crash Avoidance System (IFTCAS) |  |  | 2022-01-01 | 2022-12-31 | 365
| Significant Accomplishment A | Complete System Engineering Tasks | A | 0% | 2022-01-01 | 2022-06-30 | 181
| Significant Accomplishment A.1 | Complete System Engineering Management Tasks | A.1 | 0% | 2022-01-01 | 2022-02-15 | 46
Complete
| Significant Accomplishment A.2 | Complete System Engineering Support Tasks | A.2 | 0% | 2022-02-16 | 2022-04-01 | 45
Complete
| Significant Accomplishment A.4 | Complete System Engineering Test Tasks | A.4 | 0% | 2022-04-02 | 2022-05-17
Support integration of system into Aircraft and collect data to analysis
| Significant Accomplishment A.5 | Complete System Engineering Maintenance Tasks | A.5 | 0% | 2022-05-18 | 2022-06-30
Complete
| Significant Accomplishment C | Complete Software (SW) Engineering Tasks | C | 0% | 2022-07-01 | 2022-12-31
| Significant Accomplishment C.1 | Complete SW Engineering Management Tasks | C.1 | 0% | 2022-07-01 | 2022-08-15
Complete
| Significant Accomplishment C.2 | Complete SW Engineering Support Tasks | C.2 | 0% | 2022-08-16 | 2022-10-01
Complete
| Significant Accomplishment C.4 | Complete SW Engineering Test Tasks | C.4 | 0% | 2022-10-02 | 2022-11-17
Complete
| Significant Accomplishment C.5 | Complete SW Engineering Maintenance Tasks | C.5 | 0% | 2022-11-18 | 2022-12-31
Complete
Sample phase title block | Incorporate Test Results and Associated Design Changes Into Final System
| Program Event 3 (TBD) | Program Event 3 Name (TBD) |  |  | 2023-01-01 | 2023-12-31
| Significant Accomplishment A | Complete System Engineering Tasks | A | 0% | 2023-01-01 | 2023-06-30 | 181
| Significant Accomplishment A.1 | Complete System Engineering Management Tasks | A.1 | 0% | 2023-01-01 | 2023-02-15 | 46
Complete
| Significant Accomplishment A.2 | Complete System Engineering Support Tasks | A.2 | 0% | 2023-02-16 | 2023-04-01 | 45
Complete
| Significant Accomplishment A.3 | Update Requirements for Issues in Year 2
| Significant Accomplishment A.4 | Testing updates | A.4 | 0% | 2023-04-02 | 2023-05-17
Complete
| Significant Accomplishment A.5 | Complete System Engineering Maintenance Tasks | A.5 | 0% | 2023-05-18 | 2023-06-30
Complete
| Significant Accomplishment C | Complete Software (SW) Engineering Tasks | C | 0% | 2023-07-01 | 2023-12-31
| Significant Accomplishment C.1 | Complete SW Engineering Management Tasks | C.1 | 0% | 2023-07-01 | 2023-08-15
Complete
| Significant Accomplishment C.2 | Complete SW Engineering Support Tasks | C.2 | 0% | 2023-08-16 | 2023-10-01
Complete
| Significant Accomplishment C.4 | Complete SW Engineering Test Tasks | C.4 | 0% | 2023-10-02 | 2023-11-17
Complete
| Significant Accomplishment C.5 | Complete SW Engineering Maintenance Tasks | C.5 | 0% | 2023-11-18 | 2023-12-31
| Task C.5.1.1 | Complete
Sample phase title block | Retrofit All Commercial And Military Air Vessels With CAS
| Program Event 3 Title - Program Event 3 Titile Name | Program Event3 Name |  |  | 2024-01-01 | 2024-12-31 | 366
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.